## Slide 1
Software Engineering
Weekly report “COALA”
Dorostkar Zahra
13.03.2019
Notes: 1

## Slide 2
Project CHARTER
Project goals and vision
  To create an application to organize
  The implementation method is a Mobile application.
Project description
manages all the important aspects of classes, allowing to add classes, remove class, calculate your grades, and easily access information from any class, past or present.
1
Notes: <number>

## Slide 3
1
Architecture, high level design
Notes: <number>

## Slide 4
Архитектура, техническое решение / Architecture, high level design
Used technologies and development framework:
Java
CSS3 - basis for styles
Sqlite
1

## Slide 5
Designing the Entity diagram
Designing the UML diagram
Writing the scenarios
Detailed requirements are described
Gantt chart
Основные Достижения Отчетного Периода / Key Accomplishments For Reporting Period
1

## Slide 6
Schedule Accuracy
Past Accomplishments | Plan | Actual
Architecture planning | 10-03-2020 | 13 -03-2020
Architecture designing | 10-03-2020 | 13-03-2020
Future Milestones | % | Plan | Forecast
Architecture development | 80% | 23 -03-2020 | 27-03-2020
Basic UI development | 25% | 17-04-2020 | 20-04-2020
Merging, debugging, testing | 0% | 05-05-2020 | 08-05-2020
1
Notes: Provide milestone tracking data in your own form used in project.
Use proposed table in case you have no special form for milestone tracking
<number>

## Slide 7
Implementing of Architecture of application
Completing the design
Plans for future Reporting Period
1

## Slide 8
Thanks for attention
1
Notes: <number>